## Costs + income - 928
| projected cost | actual expenditure | actual income | notes
Invited speakers (flights, hotel) +Rachel Jeantel+Chaperone | 6100 | 8788.78 |  | estimate $300/night for Wash Sq Hotel = $1200/speaker (Wed/Thu/Fri/Sat nights), HK: Erez Levon flight and hotel, Rachel & Chaperone Flights, Rachel & Chaperone Per diem of 380 for food costs and incidentals, as of 10/11, John Rickford Hotel, Rachel Jeantel hotel, $97 for Rachel Jeantel transportation to/from airport, $1580 hotel for Erez Levon
Security
10WP | 1100 | 875 |  | COMPLETE
Silver | 0 | 0 |  | Free!
10 WP Student Mixer | 225 | 225
Kimmel Security |  | 832
Rooms
Silver, Friday | 1750 | 1750 |  | COMPLETE
Silver, Sat+Sun | 0 | 0
Kimmel, Thurs | 1210 | 1210
Kimmel, Friday | 1440 | 1440
Kimmel, Saturday | 1440 | 1440
AV
Silver, Fri | 540 | 1405 |  | Total for 10/19 and 10/20 in Silver
Silver, Sat+Sun | 840 |  |  | Tech support: $70/h * 8h (Sat) + $70/h * 4h (Sun)
Kimmel, Thurs | 1000 | 1445
Kimmel, Fri |  | 290
Kimmel, Saturday | 1000 | 2870
Catering |  |  |  | est. $5k for all coffee service (breakfast + breaks) + $3k for food @ breakfast + breaks? *HK, lower since they are buying a lot from amazon, etc...
Catering, Thurs Night | 7748.25 | 7748.25
Rentals (Coat Racks) |  | 750
Catering, Fri Night | 4150.5 | 4150.5
Catering/Dance floor rental, Sat. Night | 8355 | 8355
Thu CUNY workshops: drinks | 318 | 318
Thu CUNY workshops: snacks | 555.76 | 555.76 |  | PAID on CTA
Fri/Sat/Sun coffee breaks & snacks, Breakfast, Fri/Sat/Sun | 6000 | 3441.41 |  | $1950 Bagel Bobs: PAID | 906.41 From Staples, snack etc | 1950 from Bagel Bobs | 585 - Murrays cheese platters
Sat Student Mixer drinks/snacks | 530 | 90.83 |  | Mary & Alicia P are planning to hold this in the dept. | 90.83 Alcohol | 327.70, Keg
Careers workshop, Fri | 225 | 225 |  | Order placed 10/16
Mary Expenses (TBD what they were for but student mixer and breakfast) |  | 589.26
Rentals
Posterboards | 6800 | 6800 |  | WAITING ON REFUND TO REDUCE COSTS
Tables & chairs |  |  |  | Did we have to pay for these?
Program printing | 1246.5 | 1246.5 |  | COMPLETE
Office supplies (name badges, cash boxes, receipt books, rubber bands) | 231.96 | 231.96 |  | COMPLETE
Party entertainment | 1500 | 2450 |  | COMPLETE
NWAV committee rooms/flights | 4650 | 3832 |  | Dan, Zack and Renee to stay in hotel; Dan and Zack R/T travel, $640 for Renee, $753 for food | 1377: Zack Jaggers hotel
Merchandise | 2544.38 | 2544.38 |  | Waiting for final invoice
Sponsored sessions |  |  | 1500 | ADS ($500), SECOL ($500), LabPhon ($500)
Registration |  |  | 67958 | ***now includes Epayments Fees and LVC fees, offset by the yellow lines
LVC Payments | 8000 | 7428 |  | As of 10/12, HK added these in for the sake of accuracy
Epayment Fees | 1300 | 1404.91 |  | COMPLETE
Publishers |  |  | 1100 | COMPLETE | *HK updated numbers
Dept. contribution |  |  | 7500 | COMPLETE
CAS Dean |  |  | 500 | COMPLETE
Africana Studies |  |  | 1500 | COMPLETE
Institute of African American Affairs |  |  | 300 | COMPLETE
Center for the Study of Africa and the African Diaspora |  |  | 250 | COMPLETE
Total | 70800.35 | 74732.54 | 80608
Balance | 5875.46

## OLD estimated budget
| cost | actuals | income | notes
2 invited speakers @ 2.5k each (flights, hotel) | 5000 |  |  | estimate $300/night for Wash Sq Hotel = $1200/speaker (Wed/Thu/Fri/Sat nights)
rooms, AV | 26297 |  |  | assuming we're in Vanderbilt
catering, including poster session, student mixer, & party | 52538 |  |  | using what AMP had to pay for the Law School, and (surely) lowballing alcohol costs since I have no idea
printing, easels, tables, office supplies (name badges, folders, pens, etc.) | 5000 |  |  | based on Indiana, can reduce if no paper programs. Skip tote bags. Maybe skip folders too.
party entertainment | 3000 |  |  | ???
NYU ePayments fees | 2318.3875 |  |  | 2.75% of each transaction. Will be more than this if merch is paid through via ePayments.
ASL interpreting | 5000 |  |  | based on Vancouver. May not be needed but may as well be safe. May be even more; this is the cost of 2 ppl needing it
misc. | 20000 |  |  | because something will surely cost more
sponsored sessions |  |  | 1500 | SECOL $500 arrived 5/31, ADS $500 arrived early June
registration (see below) |  |  | 81425 | almost exactly what Toronto made (in USD) despite their fees being higher
publishers |  |  | 1500 | very comparable to what Toronto & Indiana got | *HK updated numbers
workshops |  |  | 2880 | Assuming 12 participants per workshop * 6 workshops * $40 each (Madison charged $30 each) | *HK Workshops should yield more income
dept. contribution |  |  | 15000
Lisa Coleman, Africana Studies, Dean's Office, IAAA |  |  | 11000
total | 119153.3875 |  | 113305
needed to raise | 5848.3875
Registration costs
LVC costs (via Amy Laurent at CUP, Nov 2017):
faculty, print: $52
faculty, online: $47
student, print: $30
student, online: $27
Assume:
• ca. 50% profs + 30% students w/o journal + 20% students w/journal |  |  |  | based on previous NWAV figures, though n = 2 with data available
• student reg @ 2/3 prof reg |  |  |  | seems to be what past NWAVs have done, more or less
• 450 attendees
Then: | est. # |  | journal cost | reg fee | advertised reg price | income
full-price w/print journal | 225 |  | 52 | 248 | 300 | 55800
full-price w/online journal |  |  | 47 | 248 | 295
students w/print journal | 90 |  | 30 | 95 | 125 | 8550
students w/online journal |  |  | 27 | 95 | 122
students w/o journal | 135 |  |  | 95 | 95 | 12825
unemployed/underemployed | 25 |  |  | 170 | 170 | 4250
| no idea, really^ |  |  |  |  | 81425
[6 empty] | Total EarlyBird Price Journal | Just Journal Income | Total Income
NB. Workshops not included in here. Don't see them itemized in any past budgets.
vvv the below is out of date; Eventbrite no longer has a non-profit discount and we probably won't be using them
Eventbrite fees
Toronto used Eventbrite to handle registration.
NB. Eventbrite charges fees. They are reduced if you can prove non-profit status. Must do this *before* you start selling.
You can pass the fees on to the purchaser, or pay them yourself. Toronto paid them.
Eventbrite service fees (non-profit): 2% of each ticket + $0.99 | 2% |  | 0.99
Eventbrite payment processing fees: 3% of each ticket | 3%
Total anticipated Eventbrite fees

## Actual Income
Amount | Source | Last update: 9/28/2018
500 | ADS
500 | SECOL
7500 | NYU Linguistics Department transfer, 1 & 2
500 | John Benjamins Publishing Co
500 | Association for Laboratory Phonology
100 | Duke University Press
44865 | Reg. Fees as of 9/28/2018
760 | NWAV Committee for travel award participants
55225 | Total

## Pre-registrants 1012
Paid
full-price | 118
student | 97
"discounted" | 32
travel award winner - comped | 8 | reg fees comped by Philadelphia NWAV committee
day rate ($100) | 4
parent rate ($50) | 1
workshop only ($40) | 1
total | 261
Free
NYU Linguistics (faculty, grad students, undergrad volunteers) | 52
external volunteers (CUNY & UNICAMP) | 11
workshop organizer | 7 | 6 Thu workshops + Cara S
abstract award winner | 2
plenary speaker | 2
travel award winner - non comped | 1 | Philadelphia NWAV committee would only comp 8 reg fees but committee chose 9 winners
total | 75
Workshops | numbers as of 10/11 from RegComm emails to organizers
Computational Sociolinguistics | 36 | room capacity 40, closed workshop preemptively, expect to sell out
Best Practices in Sociophonetics | 28
Language Variation Suite Toolkit | 25
ISCAN | 24
Pedagogical Issues | 14
Eye-tracking for LVC research | 8
total | 135

## Room costs -- Thursday
Event | Location | Cost
Registration, food (all day) | 9th floor hallway, CUNY | 0
6 workshops (2 sessions x 3 per session) | Room 9205, 9206, 9207, CUNY | 0
Plenary (Levon) | TBD. Tishman Aud? Cantor Film Center? | 910 | <- this is how much Tishman Aud in Vanderbilt costs
POD (Podium Microphone) |  | 62.5 | AMP had to pay this and following costs
Q&A (Question and Answer Mic) |  | 75
LAB1 (Labor/Technician) |  | 50
PRES (PowerPoint Setup) |  | 50
Reception (in honor of JVS) | TBD. Greenberg Lounge? | 910 | <- cost of Greenberg Lounge
2057.5

## Catering costs -- Thursday
Need one coffee break between workshops. CUNY suggested just picking up coffee & bagels and bringing them in.
Workshop rooms are meant to accommodate 25 ppl. Maybe could squeeze to 30?
(30 * 3) * 2 = 180 ppl
One Dunkin box o' joe @ $16 serves 10 * 18 = | 288
Brooklyn Bagels catering: $7pp | 1260
catering costs, reception (snacks, wine, bartenders) | 8000 | no idea!
9548

## Room costs -- Friday
If sessions at Vanderbilt:
Event | Location | Cost
Registration, food, publishers (all day) | Greenberg Lounge | 2275
4 parallel sessions, from 9am–5:40pm | Classrooms | 5250
CBS Flat Rate - University/External |  | 250 | I'm not sure what this is, but AMP had to pay it
LAB1 (Labor/Technician) |  | 200 | AMP had to pay this, not sure if we would
PRES (PowerPoint Setup) |  | 350 | AMP had to pay this, not sure if we would
Poster session | TBD. Rosenthal Pavilion? | 675
Student mixer | Ling Dept., 1st floor | 0
9000
If sessions at Kimmel:
Event | Location | Cost
Registration, food, publishers (all day) | Kimmel Grand Hall? | 785 | though the website doesn't say how long you get it at this cost
4 parallel sessions, from 9am–5:40pm | Classrooms | 2800
AV, tech (presumed) |  | 1000
Poster session | TBD. Rosenthal Pavilion? | 675
Student mixer | Ling Dept., 1st floor | 0
5260

## Catering costs -- Friday
Costs are based on prices for Law School catering as given to AMP 2017
hot drinks, all day service | 8 | 450 | 3600
morning break - fruit | 6 | 450 | 2700
afternoon break - brownies | 4 | 450 | 1800
waitstaff | 364 | 3 | 1092 | AMP only needed 2, assuming we will need more
student mixer booze, snacks |  |  | 1000 | just a guess
catering costs, poster session (snacks, wine, bartenders) |  |  | 8000 | no idea!
18192

## Room costs -- Saturday
If sessions at Vanderbilt:
Event | Location | Cost
Registration, food, publishers (all day) | Greenberg Lounge | 2275
4 parallel sessions, from 9am–5:40pm | Classrooms | 5250
CBS Flat Rate - Weekend University/External |  | 500 | I'm not sure what this is, but AMP had to pay it
LAB1 (Labor/Technician) |  | 200 | AMP had to pay this, not sure if we would
PRES (PowerPoint Setup) |  | 350 | AMP had to pay this, not sure if we would
NYU Guard Services |  | 539
Plenary (Rickford) | Tishman Aud | 910
POD (Podium Microphone) |  | 62.5
Q&A (Question and Answer Mic) |  | 75
Party | TBD. Rosenthal? | 675
10836.5
If sessions at Kimmel:
Event | Location | Cost
Registration, food, publishers (all day) | Kimmel Grand Hall? | 785 | though the website doesn't say how long you get it at this cost
4 parallel sessions, from 9am–5:40pm | Classrooms | 2800
AV, tech (presumed) |  | 1000
Plenary (Rickford) | Eisner & Lubin Aud | 700
Microphones |  | 150 | just a guess
Party | TBD. Rosenthal? | 675
6110

## Catering costs -- Saturday
Costs are based on prices for Law School catering as given to AMP 2017
hot drinks, all day service | 8 | 450 | 3600
morning break - fruit | 6 | 450 | 2700
afternoon break - brownies | 4 | 450 | 1800
waitstaff | 364 | 3 | 1092 | AMP only needed 2, assuming we will need more
weekend chef/managerial fee | 275 | 1 | 275 | AMP had to pay this
catering costs, party (snacks, wine, bartenders) |  |  | 8000 | no idea!
17467

## Room costs -- Sunday
If sessions at Vanderbilt:
Event | Location | Cost
Registration, food, publishers (all day) | Greenberg Lounge | 910
4 parallel sessions, from 9am–5:40pm | Classrooms | 2100
CBS Flat Rate - Weekend University/External |  | 500 | I'm not sure what this is, but AMP had to pay it
LAB1 (Labor/Technician) |  | 200 | AMP had to pay this, not sure if we would
PRES (PowerPoint Setup) |  | 350 | AMP had to pay this, not sure if we would
NYU Guard Services |  | 343
4403
If sessions at Kimmel:
Event | Location | Cost
Registration, food, publishers (all day) | Kimmel Grand Hall? | 785 | again, the website doesn't say how long you get it at this cost -- could be less for a half day
4 parallel sessions, from 9am–5:40pm | Classrooms | 1120
AV, tech (presumed) |  | 1000
2905

## Catering costs -- Sunday
Costs are based on prices for Law School catering as given to AMP 2017
hot drinks, all day service | 8 | 450 | 3600 | AMP had to pay the "all day" cost even though they just needed it from 9am–1pm
morning break - fruit | 6 | 450 | 2700
waitstaff | 252 | 3 | 756 | AMP only needed 2, assuming we will need more
weekend chef/managerial fee | 275 | 1 | 275 | AMP had to pay this
7331