OCT 10 NWAV MTG MINUTES

ST to get ADS commitment letter

French -400 yrs in Ontario **AJV**

 Institut Franco-Ontarien

 French Depts.

Provincial funding?

 Any events already planned? Is our French Dept. gonna do something?

MH to ask Guelph, and various York offices

NSF

SSHRC Connection due Nov. 1

NN will make PDF of letters

We will all be collaborators.

Excel document w/ sections

 Will put in Dropbox as .docs to edit

 NN to do budget: input, output

 AJV to give stats for # Canadians and CanCon

 GOAL: talk about conf as a whole

James as co-app to get $$ to York ? What are rules? Requirements? NO! NOT NECESSARY.

Poster session w/ QR codes to get abstract and/or PDF of poster (LeAnn’s idea)

And PPTs?

QRstuff.com

LGCU (Grad student org. for LIN)

SLUGS(Undergrad student org. for LIN)

Dean’s Initiative Fund

Thursday afternoon at York – MH is working on.

Workshops

 Sali’s was/were workshop (a discourse analyst? Anna-Maria Trester?)

 Gerard – classroom data (but not innovative)

 Greg co-variation Cathleen & Sali, Emilie LeBlanc,

Sociophonetics “best practices” Marianna & Malcah (ongoing but may be not fresh)

“marketing” technology that we create (Alex, UCL, Kisler&Fruewald)

MEM – JW & MM and a stats-head, Gries, Joe Fruehwald, Joy Roy – maybe w/ reporting on same data w/ GV and MEM

|  |  |  |
| --- | --- | --- |
| SSHRCC sections to be copied to site | What ST has done 10-10-14 |  Who to do |
| **Identification** | Done |  |
| **Activity details** | Done |  |
| **Participants** | We need to decide if there are co-applicants or collaborators. Implicates doing SSHRC CV | YES.  |
| **Event Presenters** | Mostly done, but need to reduce abstracts to 100-150 words (no word from Johnson, Meyerhoff) | AJV |
| **Letters of support** | To be uploaded … but which ones? Where? Names? | NN |
| **Summary** | Drafted | JW |
| **Expected outcomes** | Could add more here | PA |
| **Description of project** | Drafted | all read instructions and content |
| Other support | Perhaps not relevant? | NN |
| **Training and mentoring** | Partially drafted | all |
| **KMB plan** | Partially drafted. Needs work. Milestone in the year to come. CFP date, etc. | all |
| **Funds (SSHRC)** |   | NN |
| **Funds (Other)** | NSF, SLUGS, LGCU, Dean's Initiative | NN |
| **Budget justification** | Partially drafted; needs work\*\* | NN |
| **List of references** |  | NN |
| Enviromental impact | Not relevant |   |
| CEAA pre-screening | Not relevant |   |
| **Research Contributions (Applicant)** |  | ST |
| Research-Creation | Not relevant |   |
| **Relevant Experience** | Drafted, with Tagliamonte as Applicant |  |
| Suggested assessors | We have a list now |  |